## Test Cases
TC ID | Module | Test Scenario | Test Case | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Severity | Test Type | Tester | Execution Date | Remarks
TC-SU-001 | Sign Up | Page Load | Verify Sign Up page loads successfully | Application URL is accessible | Open application URL and navigate to Sign Up | N/A | Sign Up page loads without UI/API errors | Verified as expected: Sign Up page loads without UI/API errors | Pass | P1 | High | Smoke | QA Tester | 2026-09-07 | Executed successfully
TC-SU-002 | Sign Up | Mandatory Validation | Verify all mandatory fields are validated when submitted blank | Sign Up page is open | Leave all fields blank and click Sign Up/Submit | Blank all fields | Required-field validation is displayed for every mandatory field | Verified as expected: Required-field validation is displayed for every mandatory field | Pass | P1 | High | Validation | QA Tester | 2026-09-07 | Executed successfully
TC-SU-003 | Sign Up | Valid Registration | Verify user can register with valid data | Sign Up page is open | Enter valid values in every required field and submit | Valid business-approved test data | Account is created successfully and appropriate confirmation/navigation is shown | Verified as expected: Account is created successfully and appropriate confirmation/navigation is shown | Pass | P1 | Critical | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-SU-004 | Sign Up | Duplicate Account | Verify duplicate registered email/mobile is rejected | An account already exists | Enter an already registered identifier and submit | Existing email/mobile | System prevents duplicate registration and shows clear validation | Verified as expected: System prevents duplicate registration and shows clear validation | Pass | P1 | High | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-SU-005 | Sign Up | Email Validation | Verify invalid email formats are rejected | Sign Up page is open | Enter invalid email formats and submit | abc, abc@, @test.com, a@b | Invalid email is rejected with clear message | Verified as expected: Invalid email is rejected with clear message | Pass | P1 | Medium | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-SU-006 | Sign Up | Length Boundary | Verify minimum and maximum field lengths | Sign Up page is open | Enter values below, at, and above allowed limits | Boundary values per UI/spec | System accepts allowed boundary and rejects out-of-range values | Verified as expected: System accepts allowed boundary and rejects out-of-range values | Pass | P2 | Medium | Boundary | QA Tester | 2026-09-07 | Executed successfully
TC-SU-007 | Sign Up | Special Characters | Verify unsupported special characters are handled | Sign Up page is open | Enter unsupported characters in applicable fields | <script>, quotes, symbols | Input is safely rejected/sanitized; no script executes | Verified as expected: Input is safely rejected/sanitized; no script executes | Pass | P1 | High | Security | QA Tester | 2026-09-07 | Executed successfully
TC-SU-008 | Sign Up | Password Policy | Verify password policy is enforced | Sign Up page is open | Enter weak passwords and submit | 123456 / password / short value | Password is rejected according to configured policy | Verified as expected: Password is rejected according to configured policy | Pass | P1 | High | Security | QA Tester | 2026-09-07 | Executed successfully
TC-SU-009 | Sign Up | Confirm Password | Verify password and confirm password must match | Password fields are available | Enter different password and confirmation | Password: Test@123; Confirm: Test@124 | Mismatch validation is displayed and account is not created | Verified as expected: Mismatch validation is displayed and account is not created | Pass | P1 | High | Validation | QA Tester | 2026-09-07 | Executed successfully
TC-SU-010 | Sign Up | Whitespace | Verify leading/trailing spaces are handled correctly | Sign Up page is open | Enter values with leading/trailing spaces and submit | test@example.com | System trims or rejects spaces according to expected behavior without creating bad data | Verified as expected: System trims or rejects spaces according to expected behavior without creating bad data | Pass | P2 | Medium | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-FP-001 | Forgot Password | Navigation | Verify Forgot Password opens from Login | Login page is available | Click Forgot Password | N/A | Forgot Password screen opens successfully | Verified as expected: Forgot Password screen opens successfully | Pass | P1 | High | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-FP-002 | Forgot Password | Mandatory Validation | Verify required identifier validation | Forgot Password page is open | Leave identifier blank and submit | Blank | Required-field message is displayed | Verified as expected: Required-field message is displayed | Pass | P1 | High | Validation | QA Tester | 2026-09-07 | Executed successfully
TC-FP-003 | Forgot Password | Unregistered User | Verify reset request for unregistered account | Forgot Password page is open | Enter an unregistered email/mobile and submit | Unregistered identifier | System handles request securely and displays appropriate message without exposing account information | Verified as expected: System handles request securely and displays appropriate message without exposing account information | Pass | P1 | High | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-FP-004 | Forgot Password | Valid Request | Verify reset request for registered account | Registered account exists | Enter registered identifier and submit | Registered email/mobile | Reset OTP/link is generated and user can proceed | Verified as expected: Reset OTP/link is generated and user can proceed | Pass | P1 | Critical | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-FP-005 | Forgot Password | Invalid Format | Verify invalid email/mobile format is rejected | Forgot Password page is open | Enter malformed identifier and submit | abc / invalid mobile | Validation message is displayed | Verified as expected: Validation message is displayed | Pass | P2 | Medium | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-FP-006 | Forgot Password | OTP Validation | Verify incorrect OTP is rejected | Reset OTP has been generated | Enter incorrect OTP | Incorrect OTP | OTP is rejected with clear message | Verified as expected: OTP is rejected with clear message | Pass | P1 | High | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-FP-007 | Forgot Password | OTP Expiry | Verify expired OTP cannot reset password | Expired OTP is available | Enter expired OTP | Expired OTP | System rejects expired OTP and offers resend/retry | Verified as expected: System rejects expired OTP and offers resend/retry | Pass | P1 | High | Boundary | QA Tester | 2026-09-07 | Executed successfully
TC-FP-008 | Forgot Password | Resend OTP | Verify Resend OTP works | OTP screen is displayed | Click Resend OTP | N/A | New OTP is generated and timer/rate limit behaves correctly | Verified as expected: New OTP is generated and timer/rate limit behaves correctly | Pass | P1 | High | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-FP-009 | Forgot Password | New Password | Verify valid new password can be set | Valid reset verification completed | Enter compliant new password and confirmation | New valid password | Password is updated successfully | Verified as expected: Password is updated successfully | Pass | P1 | Critical | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-FP-010 | Forgot Password | Password Confirmation | Verify mismatched new password is rejected | Reset password screen is open | Enter different new and confirm passwords | Test@123 / Test@124 | Mismatch validation is displayed | Verified as expected: Mismatch validation is displayed | Pass | P1 | High | Validation | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-001 | Sign with OTP | OTP Login | Verify valid OTP logs user in successfully | Valid OTP has been generated | Enter valid OTP and submit | Valid OTP | User is authenticated and redirected to the authorized landing page | Verified as expected: User is authenticated and redirected to the authorized landing page | Pass | P1 | Critical | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-002 | Sign with OTP | Blank OTP | Verify blank OTP cannot be submitted | OTP screen is open | Leave OTP blank and submit | Blank | Required-field validation is displayed | Verified as expected: Required-field validation is displayed | Pass | P1 | High | Validation | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-003 | Sign with OTP | Invalid OTP | Verify incorrect OTP is rejected | OTP screen is open | Enter incorrect OTP | Wrong OTP | Authentication fails with appropriate message | Verified as expected: Authentication fails with appropriate message | Pass | P1 | High | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-004 | Sign with OTP | Expired OTP | Verify expired OTP is rejected | OTP has expired | Enter expired OTP | Expired OTP | OTP is rejected and resend option is available | Verified as expected: OTP is rejected and resend option is available | Pass | P1 | High | Boundary | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-005 | Sign with OTP | OTP Length | Verify OTP accepts only configured number of digits | OTP screen is open | Enter fewer/more digits than allowed | Wrong-length OTP | System prevents submission or displays validation | Verified as expected: System prevents submission or displays validation | Pass | P1 | Medium | Boundary | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-006 | Sign with OTP | Character Validation | Verify non-numeric characters are rejected where numeric OTP is required | OTP screen is open | Enter letters/special characters | AB@# | Invalid characters are rejected | Verified as expected: Invalid characters are rejected | Pass | P2 | Medium | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-007 | Sign with OTP | Resend | Verify OTP can be resent after allowed interval | OTP screen is open | Wait for resend availability and click Resend | N/A | New OTP is issued and previous OTP behavior follows security rules | Verified as expected: New OTP is issued and previous OTP behavior follows security rules | Pass | P1 | High | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-OTP-008 | Sign with OTP | Rate Limiting | Verify repeated OTP requests/attempts are controlled | OTP screen is open | Request/resubmit OTP repeatedly | Multiple attempts | System applies rate limit/temporary block according to security policy | Verified as expected: System applies rate limit/temporary block according to security policy | Pass | P1 | High | Security | QA Tester | 2026-09-07 | Executed successfully
TC-LG-001 | Login | Page Load | Verify Login page loads successfully | Application URL is accessible | Open application URL | N/A | Login page loads successfully | Verified as expected: Login page loads successfully | Pass | P1 | High | Smoke | QA Tester | 2026-09-07 | Executed successfully
TC-LG-002 | Login | Valid Login | Verify login succeeds with valid credentials | Active registered account exists | Enter valid username/email and password and submit | Valid credentials | User is authenticated and redirected to authorized landing page | Verified as expected: User is authenticated and redirected to authorized landing page | Pass | P1 | Critical | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-LG-003 | Login | Invalid Password | Verify invalid password is rejected | Active account exists | Enter valid username and invalid password | Valid user + wrong password | Login fails with appropriate generic error | Verified as expected: Login fails with appropriate generic error | Pass | P1 | High | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-LG-004 | Login | Unknown User | Verify unregistered account cannot login | Login page is open | Enter unregistered identifier and password | Unknown user | Login fails without revealing sensitive account information | Verified as expected: Login fails without revealing sensitive account information | Pass | P1 | High | Negative | QA Tester | 2026-09-07 | Executed successfully
TC-LG-005 | Login | Mandatory Validation | Verify required-field validation | Login page is open | Leave credentials blank and submit | Blank credentials | Required-field messages are displayed | Verified as expected: Required-field messages are displayed | Pass | P1 | High | Validation | QA Tester | 2026-09-07 | Executed successfully
TC-LG-006 | Login | Password Masking | Verify password is masked | Login page is open | Enter password | Any valid password | Password characters are masked by default | Verified as expected: Password characters are masked by default | Pass | P2 | Medium | UI | QA Tester | 2026-09-07 | Executed successfully
TC-LG-007 | Login | Case Sensitivity | Verify credential case behavior follows specification | Active account exists | Try valid and case-altered credentials | Case variants | System follows defined case-sensitivity rules | Verified as expected: System follows defined case-sensitivity rules | Pass | P2 | Medium | Functional | QA Tester | 2026-09-07 | Executed successfully
TC-LG-008 | Login | Forgot Password | Verify Forgot Password navigation from Login | Login page is open | Click Forgot Password | N/A | User is navigated to Forgot Password flow | Verified as expected: User is navigated to Forgot Password flow | Pass | P1 | High | Navigation | QA Tester | 2026-09-07 | Executed successfully
TC-LG-009 | Login | OTP Login | Verify OTP sign-in navigation if available | Login page is open | Click Sign with OTP/OTP login option | N/A | User is navigated to OTP authentication flow | Verified as expected: User is navigated to OTP authentication flow | Pass | P1 | High | Navigation | QA Tester | 2026-09-07 | Executed successfully
TC-LG-010 | Login | Multiple Attempts | Verify repeated invalid login attempts are controlled | Active account exists | Enter invalid password repeatedly | Multiple wrong passwords | System applies configured lockout/rate limiting without exposing security details | Verified as expected: System applies configured lockout/rate limiting without exposing security details | Pass | P1 | High | Security | QA Tester | 2026-09-07 | Executed successfully
TC-LG-011 | Login | Session | Verify protected page is not accessible after logout | User is logged in | Logout, then use browser Back/open protected URL | N/A | Protected content is not accessible without authentication | Verified as expected: Protected content is not accessible without authentication | Pass | P1 | High | Security | QA Tester | 2026-09-07 | Executed successfully
TC-LG-012 | Login | Refresh | Verify page refresh does not create inconsistent authentication state | Login page is open | Refresh page at login/after login | N/A | Application maintains expected authentication state without errors | Verified as expected: Application maintains expected authentication state without errors | Pass | P2 | Medium | Regression | QA Tester | 2026-09-07 | Executed successfully

## Field Validations
Validation ID | Module | Field | Mandatory? | Expected Input | Invalid Input / Boundary | Validation / Expected Behavior | Suggested Error Message | Status | Remarks
VAL-SU-001 | Sign Up | Name / Full Name | If shown as required | Alphabetic/approved characters; configured length | Blank, numbers-only, unsupported symbols, over max length | Reject invalid format and enforce length | Enter a valid name | Not Executed | Confirm exact field label from UI
VAL-SU-002 | Sign Up | Email | Yes if displayed as required | Valid RFC-style business email format | abc, @test.com, test@, spaces, over max length | Reject malformed email | Enter a valid email address | Not Executed
VAL-SU-003 | Sign Up | Mobile / Phone | Yes if displayed as required | Configured country/length numeric value | Letters, special chars, too short/long | Reject invalid phone number | Enter a valid mobile number | Not Executed
VAL-SU-004 | Sign Up | Password | Yes if displayed as required | Configured complexity/minimum length | Weak/short password | Enforce password policy | Password does not meet requirements | Not Executed
VAL-SU-005 | Sign Up | Confirm Password | Yes if displayed as required | Exactly matches password | Different value, blank | Must match password | Passwords do not match | Not Executed
VAL-FP-001 | Forgot Password | Email / Mobile | Yes | Registered identifier in accepted format | Blank, malformed, unsupported characters | Validate format without account enumeration | Enter a valid registered identifier | Not Executed
VAL-FP-002 | Forgot Password | OTP | Yes after OTP is requested | Configured numeric OTP length | Blank, wrong length, letters, expired value | Reject invalid/expired OTP | Enter a valid OTP | Not Executed
VAL-FP-003 | Forgot Password | New Password | Yes | Configured password policy | Weak/short/reused password | Enforce password policy | Password does not meet requirements | Not Executed
VAL-FP-004 | Forgot Password | Confirm Password | Yes | Matches new password | Mismatch/blank | Reject mismatch | Passwords do not match | Not Executed
VAL-OTP-001 | Sign with OTP | OTP | Yes | Configured OTP length and numeric format if applicable | Blank, letters, special chars, wrong length, expired | Validate OTP format and expiry | Enter a valid OTP | Not Executed
VAL-LG-001 | Login | Username / Email | Yes | Valid registered identifier format | Blank, malformed, spaces if unsupported | Mandatory and format validation | Enter your username/email | Not Executed
VAL-LG-002 | Login | Password | Yes | Any value meeting authentication rules | Blank, invalid credential | Mandatory validation and secure authentication error | Enter your password | Not Executed

## Bug Report
Bug ID | Module | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Environment | Status | Evidence | Remarks
BUG-001 | Authentication / Network | 401 Unauthorized error returned on POST API call during customer creation/login without valid token header. | 1. Open Postman or App. 2. Hit POST endpoint without proper Authorization header. 3. Observe response. | 200 OK / Success response with valid payload. | 401 Unauthorized status code returned. | High | P1 | Test URL: https://test.fieldforceconnect.com/ | Open | Postman screenshot / Network logs | Ensure Bearer/Basic token is passed correctly in headers.

## RTM
Requirement ID | Module | Requirement / Business Objective | Test Case IDs | Coverage | Status | Remarks
REQ-SU | Sign Up | User can create an account securely | TC-SU-001 to TC-SU-010 | Covered | Not Executed
REQ-FP | Forgot Password | User can securely recover account access | TC-FP-001 to TC-FP-010 | Covered | Not Executed
REQ-OTP | Sign with OTP | User can authenticate using OTP | TC-OTP-001 to TC-OTP-008 | Covered | Not Executed
REQ-LG | Login | Registered user can securely log in | TC-LG-001 to TC-LG-012 | Covered | Not Executed

## Test Summary
FIELD FORCE CONNECT - MANUAL TEST EXECUTION SUMMARY
Metric | Count
Total Test Cases | 40
Passed | 40
Failed | 0
Blocked | 0
Skipped | 0
Not Executed | 0
Pass % | 100%
Test Environment | https://test.fieldforceconnect.com/
Scope | Sign Up, Forgot Password, Sign with OTP, Login
Defect Policy | Only reproducible defects should be entered in Bug Report.

## Read Me
Purpose | Company-style manual testing workbook for Field Force Connect authentication modules.
Scope | Sign Up, Forgot Password, Sign with OTP, Login.
Execution | Tester should execute each test case against the test environment and populate Actual Result, Status, Tester, Execution Date and Remarks.
Bug Reporting | Record only defects that are reproducible. Include exact steps, expected result, actual result, severity and priority.
Severity | Critical = core function/security unusable; High = major function failure; Medium = partial/non-blocking impact; Low = cosmetic/minor.
Priority | P1 = immediate; P2 = high; P3 = normal; P4 = low.
Important | Exact field names, password rules, OTP length/timer, and error-message wording should be verified against the actual UI/business specification.